## 1. Payment Request Letter
BIG IDEAS LETTERHEAD (Let's pretend it's here) 12/31/2019 Association of Bay Area Governments James Muller San Francisco Estuary partnership 375 Beale Street, Suite 700 San Francisco, CA 94105 Re: ABAG/DWR Agreement #4600013248, DACI Project #: 00 Project Name: Big Ideas Project Invoice#: 1 Requested Payment: $8,045.21 Invoice Period of Time Covered: August 28, 2019 - November 30, 2019 Please remit payment check to: SFEP Dream Team 123 Starboard Way Venus, CA 12345 Grant activities provided during the time period referenced above are evidenced in the attached invoice and progress report, which include services as required for completion and approval of Grant Work Activity 2: DACTIP Phase I - Needs Assessments, Capacity Building & IRWM Project Development, and Coordinating Committee Integration. Total Grant Share for this Invoice: $8,045.21 Sincerely, Josh Bradt

## 2. Invoice Documentation Sumary
Invoice Documentation Summary Table |  |  |  | INVOICE # | 1
Grantee: Association of Bay Area Governments
IRWM Grant #4600013248 |  |  |  | Date of Invoice: | 2019-12-31
Local Project Sponsor: | Association of Bay Area Governments |  |  | Invoicing Period: | August 28 - November 30, 2019
Project # | 00
Project Partner | SFEP Dream Team
Invoice Description | Notes | Invoice Number | Invoice Date | Grant Amount Billed | Invoice Amount | Invoice Packet Page Number
Activity 2: DACTIP Phase I - Needs Assessments, Capacity Building & IRWM Project Development, and Coordinating Committee Integration
Task 1: Project Administration
Personnel Hours | See personnel hours summary table | n/a | n/a | 900 | 900
Travel | BART Travel to kickoff meeting 10/11/2019 | n/a | n/a | 12.9 | 12.9
SUBTOTAL |  |  |  | 912.9 | 912.9
Task 2: Needs Assessment/Capacity Building
Personnel Hours | See personnel hours summary table | n/a | n/a | 3300 | 3300
CostCo | Flipchart for outreach event | 123987 | 2019-08-28 | 25.31 | 84.51
SUBTOTAL |  |  |  | 3325.31 | 3384.51
Task 3: Project Development
Personnel Hours | See personnel hours summary table | n/a | n/a | 2582 | 2582
SUBTOTAL |  |  |  | 2582 | 2582
Task 4: Coordinating Committee and Agency Coordination and Integration
Personnel Hours | See personnel hours summary table | n/a | n/a | 1225 | 1225
SUBTOTAL |  |  |  | 1225 | 1225
GRAND TOTAL |  |  |  | 8045.21 | 8104.41
Add rows as necessary to capture all expenses.

## 3.Personnel Hours Summary
Personnel Hours Summary Table |  | INVOICE # | 1
Grantee: Association of Bay Area Governments
IRWM Grant #4600013248 |  | Date of Invoice: | 2019-12-31
Local Project Sponsor: | Association of Bay Area Governments | Invoicing Period: | August 28 - November 30, 2019
Project # | 00
Project Partner | SFEP Dream Team
Employee | Work Performed | Hours | Hourly Rate* | Total
Activity 2: DACTIP Phase I - Needs Assessments, Capacity Building & IRWM Project Development, and Coordinating Committee Integration
Task 1: Project Administration
James Muller | Progress report writing | 10 | 25 | 250
Josh Bradt | Invoicing | 4 | 50 | 200
Patty Lupone | Report and invoice review | 15 | 30 | 450
SUBTOTAL |  |  |  | 900
Task 2: Needs Assessment/Capacity Building
Patti LaBelle | Outreach, surveys, community engagement | 30 | 35 | 1050
Jennifer Lopez | Outreach, surveys, community engagement | 25 | 42 | 1050
James Muller | Capacity building | 30 | 25 | 750
Josh Bradt | Note taking and Needs Assessment writing | 5 | 50 | 250
Peppermint Patty | Translator at community events | 5 | 40 | 200
SUBTOTAL |  |  |  | 3300
Task 3: Project Development
Patti LaBelle | Prepared for community meeting to discuss solutions | 5 | 35 | 175
Jennifer Lopez | Supported community meeting to discuss solutions | 46 | 42 | 1932
James Muller | Supported community meeting to discuss solutions | 9 | 25 | 225
Josh Bradt | Supported community meeting to discuss solutions | 5 | 50 | 250
SUBTOTAL |  |  |  | 2582
Task 4: Coordinating Committee and Agency Coordination and Integration
Patti LaBelle | Attended CC meeting to provide feedback in person | 5 | 35 | 175
Jennifer Lopez | Compiled and submitted written feedback from community members | 25 | 42 | 1050
SUBTOTAL |  |  |  | 1225
GRAND TOTAL |  |  |  | 8007

## Billing Rates Support Lang
10/11/2019 Association of Bay Area Governments James Muller San Francisco Estuary partnership 375 Beale Street, Suite 700 San Francisco, CA 94105 Subject: Big Ideas Project IRWM Agreement No. 4600013248 Personnel Billing Rates Notification Dear Mr. James Muller, SFEP Dream Team will be providing personnel services for the Big Ideas Project funded through the Proposition 1 Disadvantaged Community Involvement Grant, Agreement No. 4600013248. This letter is being provided to support the rates of the SFEP Dream Team staff that will be working on the project. Should the staff or rates change, a written notification will be provided. The hourly rate is comprised of the salary plus benefits. The salary comprises 73% of the billable rate while the benefits comprise the remaining 27%. The following staff will work on the project at the following rates:
***** Only submit the billable rates letter with your first invoice *****
Employee Name | Classification | Effective Dates | Hourly Labor Rate
James Muller | Project Manager | 4/25/2019 - Present | 25
Josh Bradt | Outreach Specialist | 4/25/2019 - Present | 50
Patti LaBelle | Accountant | 4/25/2019 - Present | 35
Patty Lupone | Outreach Specialist | 4/25/2019 - Present | 30
Jennifer Lopez | Community Support Liason | 4/25/2019 - Present | 42
Peppermint Patty | Community Support Liason | 4/25/2019 - Present | 40
Should you have any questions or concerns, please contact Josh Bradt at (510) 778 - 6674 or at josh.bradt@sfestuary.org. Sincerely, Josh Bradt